## Data
Change Number | Change Title | Change Type | Priority | Risk Level | Status | Requested Date | Planned Start | Planned End | Actual Start | Actual End | Implementer | Approver | Category | Impact | CI Affected | Success | Incident Caused | Related Incidents | Backout Performed
CHG20250100002 | Deploy CRM hotfix for subscriber lookup performance | Normal | P2 | Low | Closed | 2024-12-31 03:01 | 2025-01-03 03:01 | 2025-01-03 07:01 | 2025-01-03 03:57 | 2025-01-03 08:20 | Maria Garcia | CAB-Weekly | Infrastructure | Medium | Campaign-Management | Yes | No |  | No
CHG20250100003 | Update proDEWUct catalog with 5G data plans | Normal | P4 | Medium | Implemented | 2024-12-25 13:14 | 2024-12-29 13:14 | 2024-12-29 18:14 | 2024-12-29 13:04 | 2024-12-29 20:12 | Sarah Johnson | IT-Manager-Alice | Application | Medium | Fraud-Detection-Engine | Yes | No |  | No
CHG20250100004 | Enable two-factor authentication for agent desktop | Normal | P3 | High | Failed | 2024-12-07 01:46 | 2024-12-11 01:46 | 2024-12-11 03:46 | 2024-12-11 01:46 | 2024-12-11 04:46 | John Smith | CAB-Emergency | Database | High | Billing-DB-Replica | No | No |  | No
CHG20250100005 | Patch Customer Portal security vulnerability CVE-2025-1234 | Standard | P3 | Low | Closed | 2024-11-27 12:17 | 2024-12-01 12:17 | 2024-12-01 18:17 | 2024-12-01 13:12 | 2024-12-01 18:25 | Emily Davis | CAB-Emergency | Infrastructure | Low | Self-Service-Portal | Yes | No |  | No
CHG20250100006 | Update fraud detection threshold parameters | Normal | P4 | Medium | Implemented | 2025-01-04 17:14 | 2025-01-07 17:14 | 2025-01-07 18:14 | 2025-01-07 17:24 | 2025-01-07 18:56 | Jennifer Martinez | IT-Manager-Alice | Network | Medium | Billing-Engine-01 | Yes | No |  | No
CHG20250100007 | Add new payment method integration for e-wallet | Normal | P3 | Low | Closed | 2024-12-07 04:15 | 2024-12-12 04:15 | 2024-12-12 09:15 | 2024-12-12 04:59 | 2024-12-12 09:57 | John Smith | CAB-Weekly | Application | Low | Agent-Desktop-App | Yes | No |  | No
CHG20250100008 | Update customer portal UI branding refresh | Standard | P4 | High | Closed | 2024-12-18 19:04 | 2024-12-22 19:04 | 2024-12-23 02:04 | 2024-12-22 19:06 | 2024-12-23 03:25 | Lisa Anderson | CAB-Weekly | Application | Low | CRM-Core-DB-01 | Yes | Yes | INC20250104754 | No
CHG20250100009 | Update proDEWUct catalog with 5G data plans | Standard | P2 | High | Implemented | 2025-01-06 23:16 | 2025-01-11 23:16 | 2025-01-12 02:16 | 2025-01-12 00:06 | 2025-01-12 02:32 | Robert Taylor | Change-Manager-Bob | Security | Medium | Mediation-Server | Yes | No |  | No
CHG20250100010 | Patch Customer Portal security vulnerability CVE-2025-1234 | Normal | P4 | Medium | Implemented | 2024-11-22 03:59 | 2024-11-25 03:59 | 2024-11-25 08:59 | 2024-11-25 04:41 | 2024-11-25 08:19 | Michael Chen | CAB-Emergency | Database | High | Billing-Engine-02 | Yes | No |  | No
CHG20250100011 | Configure disaster recovery replication settings | Standard | P3 | Critical | Cancelled | 2024-12-07 16:55 | 2024-12-12 16:55 | 2024-12-12 23:55 |  |  | Lisa Anderson | IT-Manager-Alice | Network | Medium | Billing-DB-Replica | No | No |  | No
CHG20250100012 | Update API gateway rate limiting policies | Normal | P3 | Medium | Implemented | 2024-12-05 02:21 | 2024-12-06 02:21 | 2024-12-06 06:21 | 2024-12-06 03:21 | 2024-12-06 08:02 | David Wilson | IT-Manager-Alice | Application | Low | Payment-Gateway | Yes | Yes | INC20250102030 | No
CHG20250100013 | Deploy order management validation rules | Normal | P2 | Medium | Implemented | 2024-12-27 15:15 | 2024-12-31 15:15 | 2024-12-31 22:15 | 2024-12-31 15:40 | 2024-12-31 22:45 | Sarah Johnson | CAB-Weekly | Infrastructure | Low | CRM-App-Server-02 | Yes | No |  | No
CHG20250100014 | Upgrade Order Management API to v3.2.1 | Standard | P2 | Critical | Implemented | 2024-12-06 06:12 | 2024-12-11 06:12 | 2024-12-11 14:12 | 2024-12-11 06:41 | 2024-12-11 14:15 | John Smith | CAB-Weekly | Security | Medium | Billing-Engine-02 | Yes | Yes | INC20250119034 | No
CHG20250100015 | Implement rate limiting on self-service API | Emergency | P3 | Medium | Failed | 2024-12-17 15:30 | 2024-12-19 15:30 | 2024-12-19 22:30 | 2024-12-19 15:30 | 2024-12-19 16:30 | Robert Taylor | IT-Manager-Alice | Application | Low | CRM-Core-DB-02 | No | No |  | No
CHG20250100016 | Patch Customer Portal security vulnerability CVE-2025-1234 | Normal | P4 | Low | Closed | 2024-12-28 23:34 | 2024-12-29 23:34 | 2024-12-30 05:34 | 2024-12-30 00:08 | 2024-12-30 06:49 | Sarah Johnson | CAB-Emergency | Infrastructure | High | Payment-Gateway | Yes | No |  | No
CHG20250100017 | Configure disaster recovery replication settings | Emergency | P3 | Low | Closed | 2024-12-06 18:38 | 2024-12-07 18:38 | 2024-12-07 20:38 | 2024-12-07 19:14 | 2024-12-07 20:58 | Michael Chen | IT-Manager-Tom | Infrastructure | High | CRM-App-Server-01 | Yes | No |  | No
CHG20250100018 | Configure monitoring alerts for SLA tracking | Emergency | P3 | Low | Implemented | 2024-11-21 14:39 | 2024-11-26 14:39 | 2024-11-26 16:39 | 2024-11-26 14:42 | 2024-11-26 16:12 | Jennifer Martinez | Change-Manager-Bob | Database | Medium | Self-Service-Portal | Yes | No |  | No
CHG20250100019 | Add new payment method integration for e-wallet | Normal | P3 | Medium | Failed | 2024-12-24 00:42 | 2024-12-29 00:42 | 2024-12-29 05:42 | 2024-12-29 00:42 | 2024-12-29 01:42 | Lisa Anderson | CAB-Emergency | Database | High | Provisioning-Gateway | No | No |  | No
CHG20250100020 | Configure load balancer for CRM failover | Normal | P2 | Medium | Closed | 2024-12-22 08:57 | 2024-12-23 08:57 | 2024-12-23 10:57 | 2024-12-23 08:32 | 2024-12-23 09:57 | James Brown | Change-Manager-Bob | Application | Low | Campaign-Management | Yes | No |  | No
CHG20250100021 | Deploy notification service enhancement for SMS retry | Standard | P3 | Medium | Implemented | 2024-11-30 17:02 | 2024-12-03 17:02 | 2024-12-03 20:02 | 2024-12-03 17:18 | 2024-12-03 19:12 | Robert Taylor | IT-Manager-Alice | Security | Medium | Billing-DB-Replica | Yes | No |  | No
CHG20250100022 | Configure load balancer for CRM failover | Standard | P2 | High | Closed | 2024-12-01 05:56 | 2024-12-05 05:56 | 2024-12-05 06:56 | 2024-12-05 06:18 | 2024-12-05 08:47 | James Brown | CAB-Weekly | Network | Low | Rating-Engine | Yes | No |  | No
CHG20250100023 | Configure load balancer for CRM failover | Standard | P3 | Medium | Implemented | 2024-12-13 09:52 | 2024-12-15 09:52 | 2024-12-15 13:52 | 2024-12-15 10:04 | 2024-12-15 14:03 | Robert Taylor | IT-Manager-Tom | Security | Low | Order-Management-API | Yes | No |  | No
CHG20250100024 | Deploy loyalty points calculation fix | Normal | P4 | Low | Closed | 2024-12-02 18:16 | 2024-12-03 18:16 | 2024-12-03 20:16 | 2024-12-03 18:26 | 2024-12-03 21:07 | John Smith | IT-Manager-Alice | Application | High | Notification-Service | Yes | No |  | No
CHG20250100025 | Deploy order management validation rules | Normal | P4 | Medium | Closed | 2025-01-03 23:47 | 2025-01-05 23:47 | 2025-01-06 05:47 | 2025-01-05 23:59 | 2025-01-06 07:26 | James Brown | IT-Manager-Tom | Infrastructure | Low | Billing-Engine-01 | Yes | No |  | No
CHG20250100026 | Enable real-time usage alerts for prepaid | Normal | P3 | Medium | Closed | 2024-12-03 13:42 | 2024-12-07 13:42 | 2024-12-07 16:42 | 2024-12-07 14:22 | 2024-12-07 15:42 | Jennifer Martinez | IT-Manager-Alice | Infrastructure | Low | Mediation-Server | Yes | No |  | No
CHG20250100027 | Update customer portal UI branding refresh | Standard | P3 | High | Closed | 2025-01-10 23:10 | 2025-01-11 23:10 | 2025-01-12 04:10 | 2025-01-11 23:22 | 2025-01-12 03:33 | Michael Chen | CAB-Weekly | Application | High | Fraud-Detection-Engine | Yes | No |  | No
CHG20250100028 | Configure monitoring alerts for SLA tracking | Normal | P4 | High | Closed | 2025-01-09 02:29 | 2025-01-13 02:29 | 2025-01-13 06:29 | 2025-01-13 02:50 | 2025-01-13 06:31 | Sarah Johnson | IT-Manager-Alice | Application | Medium | Campaign-Management | Yes | No |  | No
CHG20250100029 | Deploy CRM dashboard performance improvement | Standard | P3 | High | Failed | 2024-12-24 14:03 | 2024-12-29 14:03 | 2024-12-29 18:03 | 2024-12-29 14:03 | 2024-12-29 15:03 | Jennifer Martinez | Change-Manager-Bob | Network | High | ProDEWUct-Catalog-Service | No | No |  | No
CHG20250100030 | Enable audit logging for payment transactions | Standard | P3 | Medium | Closed | 2025-01-13 17:28 | 2025-01-15 17:28 | 2025-01-16 01:28 | 2025-01-15 18:19 | 2025-01-16 01:38 | David Wilson | CAB-Emergency | Application | Low | Notification-Service | Yes | No |  | No
CHG20250100031 | Update provisioning gateway timeout settings | Normal | P2 | High | Closed | 2024-11-26 04:09 | 2024-11-28 04:09 | 2024-11-28 11:09 | 2024-11-28 03:47 | 2024-11-28 11:55 | James Brown | Change-Manager-Bob | Security | Low | Payment-Gateway | Yes | No |  | No
CHG20250100032 | Deploy CRM dashboard performance improvement | Standard | P4 | Medium | Closed | 2024-12-15 15:00 | 2024-12-18 15:00 | 2024-12-18 20:00 | 2024-12-18 15:23 | 2024-12-18 21:17 | David Wilson | IT-Manager-Alice | Infrastructure | Low | Agent-Desktop-App | Yes | No |  | No
CHG20250100033 | Update fraud detection threshold parameters | Normal | P3 | Low | Cancelled | 2025-01-03 12:46 | 2025-01-05 12:46 | 2025-01-05 20:46 |  |  | James Brown | CAB-Emergency | Network | Low | Order-Management-API | No | No |  | No
CHG20250100034 | Deploy CRM hotfix for subscriber lookup performance | Normal | P4 | Low | Closed | 2024-12-15 10:13 | 2024-12-19 10:13 | 2024-12-19 16:13 | 2024-12-19 10:18 | 2024-12-19 17:00 | Lisa Anderson | CAB-Emergency | Database | Medium | Self-Service-Portal | Yes | No |  | No
CHG20250100035 | Implement rate limiting on self-service API | Normal | P3 | High | Implemented | 2024-11-23 00:15 | 2024-11-25 00:15 | 2024-11-25 01:15 | 2024-11-25 00:45 | 2024-11-25 03:06 | Michael Chen | Change-Manager-Bob | Database | Medium | CRM-App-Server-02 | Yes | No |  | No
CHG20250100036 | Configure disaster recovery replication settings | Normal | P4 | Low | Failed | 2025-01-09 05:19 | 2025-01-10 05:19 | 2025-01-10 06:19 | 2025-01-10 05:19 | 2025-01-10 07:19 | David Wilson | Change-Manager-Bob | Network | Medium | Payment-Gateway | No | No |  | Yes
CHG20250100037 | Add new subscriber status in CRM workflow | Normal | P2 | Critical | Implemented | 2025-01-10 01:22 | 2025-01-15 01:22 | 2025-01-15 08:22 | 2025-01-15 02:14 | 2025-01-15 08:49 | Jennifer Martinez | CAB-Emergency | Infrastructure | Medium | Self-Service-Portal | Yes | No |  | No
CHG20250100038 | Deploy customer feedback collection moDEWUle | Normal | P2 | High | Closed | 2024-12-08 19:51 | 2024-12-13 19:51 | 2024-12-14 03:51 | 2024-12-13 20:36 | 2024-12-14 03:59 | Emily Davis | IT-Manager-Alice | Infrastructure | Medium | Customer-Portal-Web | Yes | No |  | No
CHG20250100039 | Configure monitoring alerts for SLA tracking | Normal | P3 | Low | Closed | 2024-11-22 15:54 | 2024-11-25 15:54 | 2024-11-25 18:54 | 2024-11-25 15:57 | 2024-11-25 19:21 | Emily Davis | CAB-Weekly | Application | Medium | Notification-Service | Yes | No |  | No
CHG20250100040 | Update customer portal UI branding refresh | Normal | P3 | Medium | Implemented | 2025-01-08 07:44 | 2025-01-12 07:44 | 2025-01-12 15:44 | 2025-01-12 07:51 | 2025-01-12 15:40 | Robert Taylor | IT-Manager-Tom | Infrastructure | Medium | Customer-Portal-Web | Yes | No |  | No
CHG20250100041 | Update billing cycle end-of-month processing | Normal | P3 | Low | Implemented | 2024-12-13 22:29 | 2024-12-16 22:29 | 2024-12-17 03:29 | 2024-12-16 22:23 | 2024-12-17 03:49 | Jennifer Martinez | IT-Manager-Tom | Database | High | Provisioning-Gateway | Yes | No |  | No
CHG20250100042 | Configure mediation server batch processing window | Normal | P3 | High | Implemented | 2024-12-29 09:06 | 2024-12-31 09:06 | 2024-12-31 14:06 | 2024-12-31 08:37 | 2024-12-31 15:22 | Jennifer Martinez | CAB-Weekly | Network | Medium | Mediation-Server | Yes | Yes | INC20250102787 | No
CHG20250100043 | Add new payment method integration for e-wallet | Normal | P2 | Medium | Closed | 2024-12-21 14:21 | 2024-12-23 14:21 | 2024-12-23 15:21 | 2024-12-23 14:05 | 2024-12-23 14:37 | David Wilson | CAB-Weekly | Security | Low | ProDEWUct-Catalog-Service | Yes | Yes | INC20250102757 | No
CHG20250100044 | Database index optimization for billing queries | Standard | P3 | Low | Closed | 2024-12-29 19:50 | 2025-01-03 19:50 | 2025-01-03 23:50 | 2025-01-03 20:16 | 2025-01-04 00:06 | Sarah Johnson | CAB-Emergency | Database | Low | CRM-App-Server-01 | Yes | No |  | No
CHG20250100045 | Configure disaster recovery replication settings | Normal | P3 | High | Closed | 2024-12-01 07:11 | 2024-12-06 07:11 | 2024-12-06 09:11 | 2024-12-06 08:09 | 2024-12-06 10:43 | Sarah Johnson | CAB-Emergency | Security | Medium | Self-Service-Portal | Yes | Yes | INC20250110441 | No
CHG20250100046 | Enable real-time usage alerts for prepaid | Standard | P3 | High | Implemented | 2024-12-28 21:51 | 2024-12-30 21:51 | 2024-12-31 04:51 | 2024-12-30 21:40 | 2024-12-31 04:59 | Maria Garcia | IT-Manager-Tom | Infrastructure | Medium | Order-Management-DB | Yes | Yes | INC20250106437 | No
CHG20250100047 | Update customer portal UI branding refresh | Normal | P4 | Medium | Closed | 2025-01-04 12:17 | 2025-01-09 12:17 | 2025-01-09 20:17 | 2025-01-09 12:42 | 2025-01-09 20:39 | John Smith | IT-Manager-Tom | Infrastructure | Medium | Billing-Engine-02 | Yes | Yes | INC20250108502 | No
CHG20250100048 | Update provisioning gateway timeout settings | Emergency | P3 | Medium | Closed | 2024-12-21 16:41 | 2024-12-25 16:41 | 2024-12-25 21:41 | 2024-12-25 17:32 | 2024-12-25 22:46 | Michael Chen | IT-Manager-Tom | Infrastructure | Medium | Agent-Desktop-App | Yes | No |  | No
CHG20250100049 | Implement rate limiting on self-service API | Standard | P3 | Low | Closed | 2024-12-16 17:02 | 2024-12-20 17:02 | 2024-12-20 19:02 | 2024-12-20 17:23 | 2024-12-20 20:13 | Lisa Anderson | Change-Manager-Bob | Database | Medium | CRM-Core-DB-02 | Yes | Yes | INC20250118780 | No
CHG20250100050 | Deploy notification service enhancement for SMS retry | Emergency | P4 | Medium | Closed | 2024-12-04 08:35 | 2024-12-06 08:35 | 2024-12-06 13:35 | 2024-12-06 08:20 | 2024-12-06 12:42 | John Smith | Change-Manager-Bob | Infrastructure | Low | CRM-App-Server-02 | Yes | No |  | No
CHG20250100051 | Deploy notification service enhancement for SMS retry | Normal | P3 | Low | Failed | 2024-12-20 03:41 | 2024-12-22 03:41 | 2024-12-22 11:41 | 2024-12-22 03:41 | 2024-12-22 06:41 | Emily Davis | Change-Manager-Bob | Infrastructure | High | CRM-App-Server-01 | No | No |  | No